## version
Version | Date | Changed by | Details
0.1 | 2024-09-30 | Ellis Chiang | Document created.
0.2 | 2024-10-07 | Ellis Chiang | Updated test case.
0.3

## SIT plan
No | Test case | Test item | Step no. | Step description | Expected result | Actual result | Execution date | Status (Pass/Fail)
1 | Trigger end-to-end report generation flow | Trigger ADF pipeline | 1 | In RMJ console, pick a report from the Process Definition pane which using SQL database as the data source | Report(s) generated in the target destination folder
| (With SQL server as data source) | Inject data from SQL database to Synapse SQL pool |  | - refer to the report reference tab for the report configuration
|  | Execute report logic with stored procedure | 2 | Right click on the Process Definition and select Submit
|  | Generate report to target share folder | 3 | In the Parameters tab, modify the parameter with the desired value to cater for test if necessary
reportParam:
- the date of the report to be executed (set the date if required to generate a back dated report)
- the destination folder of the report (the destination folder must be already exist)
- the recipient of the email to send (change the default email recipient to some other address if necessary)
- the output file name (change the default file name if necessary)
env :
- the environment of the report to execute (use uat for test)
|  |  | 4 | In the Time and Dates tab, select "Now"
|  |  | 5 | Click the Submit button to execute the report generation
2 | Trigger end-to-end report generation flow | Trigger ADF pipeline | 1 | In RMJ console, pick a report from the Process Definition pane which using Oracle database as the data source | Report(s) generated in the target destination folder
| (With Oracle Finance database as data source) | Inject data from Oracle database to Synapse SQL pool |  | - refer to the report reference tab for the report configuration
|  | Execute report logic with stored procedure | 2 | Right click on the Process Definition and select Submit
|  | Generate report to target share folder | 3 | In the Parameters tab, modify the parameter with the desired value to cater for test if necessary
reportParam:
- the date of the report to be executed (set the date if required to generate a back dated report)
- the destination folder of the report (the destination folder must be already exist)
- the recipient of the email to send (change the default email recipient to some other address if necessary)
- the output file name (change the default file name if necessary)
env :
- the environment of the report to execute (use uat for test)
|  |  | 4 | In the Time and Dates tab, select "Now"
|  |  | 5 | Click the Submit button to execute the report generation
3 | Trigger end-to-end report generation flow | Trigger ADF pipeline | 1 | In RMJ console, pick a report from the Process Definition pane which using Sybase database as the data source | Report(s) generated in the target destination folder
| (With Sybase database as data source) | Inject data from Sybase database to Synapse SQL pool |  | - refer to the report reference tab for the report configuration
|  | Execute report logic with stored procedure | 2 | Right click on the Process Definition and select Submit
|  | Generate report to target share folder | 3 | In the Parameters tab, modify the parameter with the desired value to cater for test if necessary
reportParam:
- the date of the report to be executed (set the date if required to generate a back dated report)
- the destination folder of the report (the destination folder must be already exist)
- the recipient of the email to send (change the default email recipient to some other address if necessary)
- the output file name (change the default file name if necessary)
env :
- the environment of the report to execute (use uat for test)
|  |  | 4 | In the Time and Dates tab, select "Now"
|  |  | 5 | Click the Submit button to execute the report generation
4 | Trigger end-to-end report generation flow | Trigger ADF pipeline | 1 | In RMJ console, pick a report from the Process Definition pane which using input files as the data source | Report(s) generated in the target destination folder
| (With input file as data source) | Inject data from input file to Synapse SQL pool |  | - refer to the report reference tab for the report configuration
|  | Execute report logic with stored procedure | 2 | Right click on the Process Definition and select Submit
|  | Generate report to target share folder | 3 | In the Parameters tab, modify the parameter with the desired value to cater for test if necessary
reportParam:
- the date of the report to be executed (set the date if required to generate a back dated report)
- the destination folder of the report (the destination folder must be already exist)
- the recipient of the email to send (change the default email recipient to some other address if necessary)
- the output file name (change the default file name if necessary)
env :
- the environment of the report to execute (use uat for test)
|  |  | 4 | In the Time and Dates tab, select "Now"
|  |  | 5 | Click the Submit button to execute the report generation
5 | Trigger end-to-end report generation flow | Trigger Process Definitions by defined orders | 1 | In RMJ console, pick a report from the Chain Definition pane | Process Definition being executed following the defined orders
| (With RMJ Chain Definition) |  |  | - refer to the report reference tab for the report configuration
|  |  | 2 | Right click on the Chain Definition and select Edit
|  |  | 3 | Click on the step which is a Process Definition to trigger ADF pipeline
|  |  | 4 | In the Parameter Mappings tab, expand the Parameters by on the blue arrow
|  |  | 5 | Modify the parameter with the desired value to cater for test if necessary
reportParam:
- the date of the report to be executed (set the date if required to generate a back dated report)
- the destination folder of the report (the destination folder must be already exist)
- the recipient of the email to send (change the default email recipient to some other address if necessary)
- the output file name (change the default file name if necessary)
env :
- the environment of the report to execute (use uat for test)
|  |  | 6 | Click Save & Close to commit the change if change has been applied
|  |  | 7 | Go back to the Chain Definition, right click and select Submit
|  |  | 8 | In the Time and Dates tab, select "Now"
|  |  | 9 | Click the Submit button to execute the report generation
|  |  | 10 | After the execution is completed successfully, navigate back to the Chain Definition tab
|  |  | 11 | Right-click on the chain definition of the report just executed
|  |  | 12 | Click on the step which is a Process Definition to trigger ADF pipeline
|  |  | 13 | In the Parameter Mappings tab, expand the Parameters by on the blue arrow
|  |  | 14 | Rollback the parameter to its default value
|  |  | 15 | Click Save & Close to commit the change if change has been applied
6 | Sending email notification with attachment | Trigger email notification when has been generated | 1 | In RMJ console, pick a report from the Process Definition pane which configured to deliver report by email with SSRS | Report(s) generated in the target destination folder and an email notification will be sent to the defined recipient address
| (With SSRS to send email notification) | Send report as attachment with email |  | - refer to the report reference tab for the report configuration
|  |  | 2 | Right click on the Process Definition and select Submit
|  |  | 3 | In the Parameters tab, modify the parameter with the desired value to cater for test if necessary
reportParam:
- the date of the report to be executed (set the date if required to generate a back dated report)
- the destination folder of the report (the destination folder must be already exist)
- the recipient of the email to send (change the default email recipient to some other address if necessary)
- the output file name (change the default file name if necessary)
env :
- the environment of the report to execute (use uat for test)
|  |  | 4 | In the Time and Dates tab, select "Now"
|  |  | 5 | Click the Submit button to execute the report generation
7 | Sending email notification with attachment | Trigger email notification when has been generated | 1 | In RMJ console, pick a report from the Chain Definition pane which configured to deliver report by email with Python | Report(s) generated in the target destination folder and an email notification will be sent to the defined recipient address
| (With Python to send customized email notification) | Send report as attachment with email |  | - refer to the report reference tab for the report configuration
|  |  | 2 | Right click on the Chain Definition and select Edit
|  |  | 3 | Click on the step which is a Process Definition to trigger ADF pipeline
|  |  | 4 | In the Parameter Mappings tab, expand the Parameters by on the blue arrow
|  |  | 5 | Modify the parameter with the desired value to cater for test if necessary
reportParam:
- the date of the report to be executed (set the date if required to generate a back dated report)
- the destination folder of the report (the destination folder must be already exist)
- the recipient of the email to send (change the default email recipient to some other address if necessary)
- the output file name (change the default file name if necessary)
env :
- the environment of the report to execute (use uat for test)
|  |  | 6 | Click Save & Close to commit the change if change has been applied
|  |  | 7 | Go back to the Chain Definition, right click and select Submit
|  |  | 8 | In the Time and Dates tab, select "Now"
|  |  | 9 | Click the Submit button to execute the report generation
|  |  | 10 | After the execution completed successfully, right click on the Chain Definition and select Edit
|  |  | 11 | Click on the step which is a Process Definition to trigger ADF pipeline
|  |  | 12 | In the Parameter Mappings tab, expand the Parameters by on the blue arrow
|  |  | 13 | Rollback the parameter to its default value
|  |  | 14 | Click Save & Close to commit the change if change has been applied
8 | Failure email notification | Trigger email alert by RMJ when ADF pipeline execution failure | 1 | In RMJ console, pick a process definition of a report | An alert meail from RMJ will be sent
| (ADF Pipeline execution failure) |  | 2 | Right click on the Process Definition and select Submit
|  |  | 3 | In the Parameters tab, modify the parameter with the desired value to cater for test
reportName:
- replace the value with a report name that does not exist
env :
- the environment of the report to execute (use uat for test)
|  |  | 4 | In the Time and Dates tab, select "Now"
|  |  | 5 | Click the Submit button to execute the report generation
9 | Failure email notification | Trigger email alert by RMJ when Python program execution failure | 1 | Connect to App Server with remote desktop | An alert meail from RMJ will be sent
| (Python execution failure) |  | 2 | Open File Explorer and navigate to folder D:\BOPython\hksyn
|  |  | 3 | Rename config.json to config.json.bak
|  |  | 4 | In RMJ console, pick a process definition of a Python program (name ended with Post_Python)
|  |  | 5 | Right click on the Process Definition and select Submit
|  |  | 6 | In the Time and Dates tab, select "Now"
|  |  | 7 | Click the Submit button to execute the report generation
|  |  | 8 | Connect to App Server with remote desktop
|  |  | 9 | Open File Explorer and navigate to folder D:\BOPython\hksyn
|  |  | 10 | Rename config.json.bak to config.json

## Report reference
# | Report name | Data source | With Process Definition defined | With Chain Definition defined | With Python for post processing | Wait Pre-ETL job from Pentaho | With report generation | Send notification by email with SSRS | Send notification and report by email with SSRS | Send notification by email with Python | Send notification and report by email with Python | Encrypt report with Python | Report tables in Synapse SQL pool | Remarks
1 | FO_CounterPartyAmendment | SQL DB | Y |  |  |  | Y |  | Y
2 | FO_DailyPropTrade | SQL DB | Y |  |  |  | Y
3 | FO_RMTradingBookActivity | SQL DB | Y |  |  |  | Y
4 | FO_USClientTradeReport | SQL DB | Y | Y | Y |  | Y |  |  |  | Y
5 | Counterparty_FullList | SQL DB | Y | Y |  | Y | Y
6 | GSB_DOIEmailNotification | SQL DB | Y | [9 empty] | Y
7 | GSB_ClientStatistics | SQL DB | Y | Y |  |  | Y | [5 empty] | Y
8 | GSB_MO_AUGST_Trades | SQL DB | Y |  |  |  | Y
9 | GSB_SFC_short_position | SQL DB | Y |  |  |  | Y
10 | DVP_Usage_BBGPrice | SQL DB | Y |  |  |  | Y | Y
11 | GSB_Outstanding_Maturity | Files & SQL DB | Y |  |  |  | Y
12 | GSB_soi_ice | SQL DB | Y |  |  |  | Y
13 | GSB_soi_tlmca | SQL DB | Y |  |  |  | Y
14 | CA_FidessaPosting | SQL DB | Y |  |  |  | Y | Y
15 | CA_GSBMHSCStockPosting | SQL DB | Y |  |  |  | Y
16 | CA_GSBPosting | SQL DB | Y |  |  |  | Y
17 | CA_LinksPosting | SQL DB | Y |  |  |  | Y
18 | FRR_Form12_NAV_Under_Management | Files | Y |  |  |  | Y | [5 empty] | Y
19 | FO_StandardReport_USClientTradeDropCopy | SQL DB | Y |  |  |  | Y
20 | FO_RMTradedInstrumentRpt | SQL DB | Y |  |  |  | Y
21 | FO_ATF_ClientFacilitationTrade | SQL DB | Y |  |  |  | Y
22 | FO_OrderTicketEmsxEquityReport | SQL DB | Y | Y | Y |  | Y | Y
23 | FO_OrderTicketEmsxFuturesReport | SQL DB | Y | Y | Y |  | Y
24 | FO_OrderTicketSinopacFuturesReport | SQL DB | Y | Y | Y |  | Y
25 | FO_OrderTicketToraFuturesReport | SQL DB | Y | Y | Y |  | Y
26 | FO_OrderTicket_Recon | Sybase & SQL DB | Y |  |  |  | Y | Y
27 | FO_Fidessa_ATF_OrderTicket_Recon | Sybase & SQL DB | Y |  |  |  | Y | Y
28 | GSB_T0_TradableSize | Files & SQL DB | Y | Y | Y |  | Y |  |  |  | Y* |  |  | Multiple reports as email attachment
29 | GSB_FailedTradeMTM | SQL DB | Y |  |  |  | Y
30 | GSB_DOI_Position_Movement | Files & SQL DB | Y | Y | Y |  | Y
31 | BO_Short_Position_SG_EQ | SQL DB | Y |  |  |  | Y | Y* | [5 empty] | Send notification email only when error record exists (tmp_err_sqeq_shortsell)
32 | GSB_DailyStampDuty | SQL DB | Y |  |  |  | Y
33 | GSB_FRR_Client_List_Report | Files & SQL DB | Y |  |  |  | Y | [5 empty] | Y
34 | GSB_CN_DailyStampDuty | SQL DB | Y |  |  |  | Y
35 | fx_devt_mth_stmt_gen | SQL DB | Y | Y | Y |  | Y |  |  | Y
36 | fx_devt_mth_stmt_distribute | SQL DB | Y | Y | Y |  | Y | Y* |  | Y | Y | Y |  | Send notification email only when error record exists (err_murex_stmt)
37 | OF_Oracle_Financial_Daily_Exchange_Rate | Oracle DB | Y |  |  |  | Y
38 | OF_SG_Daily_Exchange_Rate | Oracle DB | Y |  |  |  | Y |  | Y
39 | OF_audit_report | Oracle DB | Y |  |  |  | Y
40 | SBL_CA_Entitlement | Oracle DB | Y |  |  |  | Y
41 | GSB_Short_Sell_Report_MHSS | Oracle DB | Y |  |  |  | Y
42 | CS_DormantAccountSummary | SQL DB | Y | Y |  | Y | Y
43 | FO_StandardReport_Shortsell | Files & SQL DB | Y |  |  |  | Y
44 | fx_devt_mth_stmt_data | SQL DB | Y |  |  | Y |  | Y* |  |  |  |  | Y | Send notification email only when error record exists (err_murex_stmt)